DELTA EXCHANGE TRADING BOT

Complete Project Plan & Roadmap

97 Days  •  13 Strategies  •  5 Phases  •  $24/month when live
Exchange: Delta Exchange India  •  Capital: $1,000

# Project Overview

| Phase | Days | Goal | Key Output |
| --- | --- | --- | --- |
| Phase 1 – Local Setup | 1–7 | Bot running in paper mode | No crashes, DB has rows |
| Phase 2 – Fix Critical Issues | 8–37 | Security fixed, stops on exchange, Grafana | 14 issues resolved |
| Phase 3 – New Strategies | 38–82 | 8 new strategies built & backtested | 13 total strategies active |
| Phase 4 – Paper Validation | 83–97 | Sharpe > 0.8, DD < 8%, Win rate > 45% | Both 14-day gates pass |
| Phase 5 – Cloud Migration | 98+ | Hetzner server, 24/7 live trading | systemd + Alertmanager active |

# Phase 1 — Local Setup & First Run (Days 1–7)

Goal: See the bot running and printing live paper trades within your first week.

## Day 1 – Installation

[CRIT] Verify Python 3.12.x — run: python --version in PowerShell  (Day 1)

[CRIT] Install Poetry — pip install poetry  (Day 1)

[CRIT] Run poetry install — Wait for all libraries to download  (Day 1)

## Day 2 – Security First

⚠  DELETE all content in .env before proceeding — API keys are already exposed on GitHub

[CRIT] Rotate API keys in .env — Paste safe paper-mode template  (Day 2)

[CRIT] Register on Delta testnet — cdn-ind.testnet.deltaex.org  (Day 2)

[CRIT] Update .env with testnet keys — DELTA_EXCHANGE_ENV=testnet-india  (Day 2)

## Day 2 – First Run

[HIGH] Run in paper mode — poetry run python -m delta_exchange_bot.cli.main --mode paper  (Day 2)

[HIGH] Observe logs 30+ minutes — JSON lines should appear every 60s  (Day 2)

[HIGH] Verify DB has rows — Use SQLite Viewer extension in VS Code  (Day 2)

## Days 3–7 – Observation

[MED] Run 2+ hours daily — Note every error message  (Days 3–7)

[HIGH] Phase 1 complete gate — Bot runs 2 consecutive days without crashing  (Day 7)

# Phase 2 — Fix Critical Issues (Days 8–37)

Goal: Security fixed, all bugs corrected, exchange-native stops, Grafana live.

## Critical Severity (Days 8–13)

⚠  Fix ALL CRIT items before building any new strategy

[CRIT] Dockerfile Python 3.11 → 3.12 — One-line change  (Day 8)

[CRIT] Merge strategy/ and strategies/ packages — Two RSIScalping classes → shadow bugs  (Days 8–10)

[CRIT] Change TRADE_FREQUENCY_S 60 → 5 — Add signal_eval_every=6 setting  (Day 8)

[CRIT] Add idempotent client_order_id — SHA256(trade_id+symbol+side)  (Day 12)

## High Severity (Days 12–20)

[HIGH] Fix RSI Wilder's smoothing — Currently 7 points off vs TradingView  (Days 12–13)

[HIGH] Wire YAML config files — config/paper.yml currently ignored  (Days 10–12)

[CRIT] Add exchange-native stop orders — place_stop_limit_order() in DeltaClient  (Days 14–20)

[HIGH] Add fill confirmation polling loop — Poll until filled/rejected/timeout  (Day 13)

## Medium Severity (Days 20–26)

[MED] Add funding rate awareness — Log rate, add to fee calculation  (Days 20–24)

[MED] Add max holding period — 30-candle default = 30 min on 1m  (Days 24–26)

[MED] Persist ProtectionState to PostgreSQL — Crash-safe SL/TP recovery on restart  (Day 20)

## Monitoring (Days 26–37)

[MED] Add Grafana + Loki to docker-compose — Trading Overview + Risk + API Health  (Days 26–37)

# Phase 3 — Eight New Strategies (Days 38–82)

Goal: Build all 8 new strategies. Backtest each. Only activate if Sharpe > 0.8.

→  Only activate a strategy in live regime dispatch if backtest Sharpe > 0.8

## Priority 1 — VWAP Deviation (Days 38–42)

[HIGH] Create VWAPDeviationStrategy — Entry: price >0.5% from VWAP → mean revert  (Days 38–42)

## Priority 2 — Bollinger Squeeze (Days 43–46)

[HIGH] Create BollingerSqueezeStrategy — Detect low-vol coil before breakout  (Days 43–46)

## Priority 3 — MACD Histogram (Days 47–50)

[HIGH] Create MACDHistogramStrategy — Histogram turn + signal line cross  (Days 47–50)

## Priority 4 — Order Book Imbalance (Days 51–56)

[HIGH] Create OrderBookImbalanceStrategy — Use existing get_orderbook() REST call  (Days 51–56)

## Priority 5 — Multi-TF Confluence (Days 57–62)

[HIGH] Create MultiTimeframeFilter — 1m + 15m + 1h all must agree direction  (Days 57–62)

## Priority 6 — Funding Rate Extremes (Days 63–68)

[HIGH] Create FundingRateExtremeStrategy — Contrarian — crowded longs/shorts  (Days 63–68)

## Priority 7 — Volume-Weighted Momentum (Days 69–72)

[HIGH] Create VolumeWeightedMomentum — Replace 3-bar momentum with 10-bar × vol  (Days 69–72)

[HIGH] Delete old MomentumStrategy — strategy/momentum.py — rated 2/5  (Day 71)

## Priority 8 — S/R Breakout (Days 73–77)

[HIGH] Create SupportResistanceBreakout — 20-bar high/low + volume spike  (Days 73–77)

## Full Backtest Validation (Days 78–82)

[CRIT] Backtest all 8 strategies individually — Gate: Sharpe > 0.8 per strategy  (Days 78–79)

[CRIT] Run all 13 together 72 hours paper — Check Grafana per-strategy PnL  (Days 80–82)

# Phase 4 — Paper Validation (Days 83–97)

Goal: MANDATORY: 14 consecutive days. Both validation gates must pass.

⚠  NEVER use real money until BOTH Day 14 gates pass

## Validation Gates

[CRIT] 14-day continuous paper run — Must be continuous — no restarts  (Days 83–97)

[CRIT] Day 7: Sharpe > 0.5 — Fail = tune or disable underperformers  (Day 90)

[CRIT] Day 7: Drawdown < 6% — Hard limit — investigate if breached  (Day 90)

[CRIT] Day 14: Sharpe > 0.8 — Final gate — must pass before Phase 5  (Day 97)

[CRIT] Day 14: Win rate > 45% — Per-strategy breakdown required  (Day 97)

[CRIT] Day 14: Max drawdown < 8% — Hard limit before any real money  (Day 97)

## Tools

[HIGH] Run analyze_paper_trades.py — Weekly — per-strategy PnL breakdown  (Weekly)

[MED] Tune underperforming strategies — Ask Claude to help adjust thresholds  (As needed)

# Phase 5 — Cloud Migration (Days 98+)

Goal: Move to Hetzner, run 24/7, go live with real money.

## Hetzner Server Setup

[HIGH] Register at hetzner.com — No credit card needed for signup  (Day 98)

[HIGH] Create CX22 server — 2vCPU, 4GB RAM, Ubuntu 22.04 — ~₹320/month  (Day 98)

[HIGH] Install Python 3.12 + Docker — Same steps as local setup  (Day 99)

[CRIT] Set production .env — DELTA_EXCHANGE_ENV=prod-india, fresh keys  (Day 100)

[CRIT] Run live_preflight.py — Final sanity check before live  (Day 100)

## Going Live — Do Not Rush

⚠  Cloud paper mode must pass 48 hours before switching DELTA_MODE=live

[CRIT] Start at half paper size — DELTA_ORDER_SIZE=50  (Day 103)

[CRIT] Monitor Grafana first 4 hours — Watch for execution errors  (Day 103)

[CRIT] Confirm stop order appears in UI — Check Delta Exchange account  (Day 103)

[HIGH] Set up systemd auto-restart — systemctl enable trading-bot  (Day 104)

[HIGH] Alertmanager → Telegram alerts — Alert on: daily loss > 3%, bot crash  (Day 105)

# Strategy Registry — All 13 Strategies

| # | Strategy | Regime | Rating | Action | Phase |
| --- | --- | --- | --- | --- | --- |
| 1 | Trend Following | TRENDING | 4/5 | Keep | Existing |
| 2 | Mean Reversion | RANGING/LOW_VOL | 4/5 | Keep | Existing |
| 3 | EMA Crossover | TRENDING | 3/5 | Keep + fix | Existing |
| 4 | RSI Scalping | RANGING/HIGH_VOL | 3/5 | Fix RSI | Phase 2 |
| 5 | Momentum (3-bar) | All | 2/5 | REPLACE → #12 | Existing |
| 6 | VWAP Deviation | RANGING/LOW_VOL | TBD | Build | Phase 3 |
| 7 | Bollinger Squeeze | LOW_VOL transition | TBD | Build | Phase 3 |
| 8 | MACD Histogram | TRENDING | TBD | Build | Phase 3 |
| 9 | Order Book Imbalance | All (secondary) | TBD | Build | Phase 3 |
| 10 | Multi-TF Confluence | All (filter) | TBD | Build | Phase 3 |
| 11 | Funding Rate Extremes | HIGH_VOL | TBD | Build | Phase 3 |
| 12 | Vol-Weighted Momentum | All | TBD | Build | Phase 3 |
| 13 | S/R Breakout | TRENDING/HIGH_VOL | TBD | Build | Phase 3 |

# Known Issues — Fix Before Phase 3

| Severity | Issue | Fix Phase |
| --- | --- | --- |
| CRIT | Real API keys in .env | Phase 1 Day 2 |
| CRIT | SL/TP in memory only — lost on crash | Phase 2 |
| HIGH | Dockerfile uses Python 3.11 | Phase 2 Day 8 |
| HIGH | RSI formula wrong (~7 pts off) | Phase 2 Day 12 |
| HIGH | Duplicate strategy packages | Phase 2 Day 8 |
| HIGH | TRADE_FREQUENCY_S=60 too slow | Phase 2 Day 8 |
| MED | YAML config files ignored | Phase 2 Day 10 |
| MED | Funding rate costs ignored | Phase 2 Day 20 |
| MED | No max holding period | Phase 2 Day 24 |
| MED | No idempotent order placement | Phase 2 |
| MED | No fill confirmation loop | Phase 2 |
| MED | Two risk managers coexist | Phase 2 |
| LOW | No Grafana dashboards | Phase 2 Day 26 |
| LOW | No CI/CD pipeline | Phase 5 |

## Monthly Cost Summary

| Item | Cost | Notes |
| --- | --- | --- |
| Claude Pro | $20/month | Your AI coding partner — essential |
| Local dev (Phases 1–4) | $0 | Everything runs on your Windows machine |
| Hetzner CX22 (Phase 5) | ~₹320 (~$4)/month | Only needed for 24/7 live trading |
| Delta Exchange fees | 0.02–0.05%/trade | Maker 0.02%, taker 0.05% |
| TOTAL during dev | $20/month | Just Claude Pro |
| TOTAL when live | ~$24/month | Claude Pro + Hetzner |