## 📊 Dashboard
DELTA EXCHANGE TRADING BOT — PROJECT TRACKER
97-day roadmap ¦ 13 strategies ¦ 5 phases ¦ $24/month when live
Phase | Days | Goal | Status | Progress
Phase 1 – Local Setup | Days 1–7 | Bot running in paper mode | Done
Phase 2 – Fix Critical Issues | Days 8–37 | Security fixed, bugs corrected, Grafana live | In Progress
Phase 3 – New Strategies | Days 38–82 | 8 new strategies built and backtested | Not Started
Phase 4 – Paper Validation | Days 83–97 | Sharpe > 0.8, Drawdown < 8%, Win rate > 45% | Not Started
Phase 5 – Cloud Migration | Days 98+ | Hetzner server, systemd, live trading with $1,000 | Not Started
Key Metrics & Rules
Metric | Value |  | Rule | Detail
Total Strategies | 13 |  | Never commit .env to git | Keys are already exposed — rotate first
Capital (start) | $1,000 |  | Paper validate before live | Minimum 14 days, both gates must pass
Max Live Position Size | $50 (half paper) |  | Start at half paper size | Scale up only after first 10 live trades
Taker Fee | 0.05% / trade |  | Fix CRIT issues before Phase 3 | No point building strategies on broken code
Monthly Cost (dev) | $20 (Claude Pro) |  | Sharpe gate for new strategies | Only add to live dispatch if Sharpe > 0.8
Monthly Cost (live) | ~$24 |  | Max daily loss kill switch | 5% daily loss → bot stops all new trades

## Phase 1 – Setup
PHASE 1 – SETUP
# | Task | File / Location | Day(s) | Duration | Priority | Status | Notes
INSTALLATION
1 | Verify Python 3.12.x installed | PowerShell | Day 1 | 30 min | CRITICAL | Done | Run: python --version
2 | Install Poetry package manager | PowerShell | Day 1 | 30 min | CRITICAL | Done | Run: pip install poetry
3 | Run poetry install | Project root | Day 1 | 1 hr | CRITICAL | Done | Wait for all libraries to download
SECURITY — DO THIS BEFORE ANYTHING ELSE
4 | Rotate leaked API keys in .env | .env | Day 2 | 1 hr | CRITICAL | Done | DELETE all content, paste safe template
5 | Register on Delta testnet | cdn-ind.testnet.deltaex.org | Day 2 | 30 min | CRITICAL | Done | Get fresh key + secret
6 | Update .env with testnet credentials | .env | Day 2 | 10 min | CRITICAL | Done | DELTA_EXCHANGE_ENV=testnet-india
FIRST RUN
7 | Run bot in paper mode | cli/main.py | Day 2 | 30 min | HIGH | Done | poetry run python -m delta_exchange_bot.cli.main --mode paper
8 | Observe log output for 30 min | Terminal | Day 2 | 30 min | HIGH | Done | Look for JSON lines every 60s
9 | Verify DB has trade/signal rows | state.db | Day 2 | 15 min | HIGH | Done | Use SQLite Viewer VS Code extension
OBSERVATION (Days 3–7)
10 | Run paper mode 2+ hours daily | Terminal | Days 3–7 | Passive | MED | Done | Note any error messages
11 | Confirm bot runs 2 consecutive days clean | Terminal | Day 7 | – | HIGH | Done | Phase 1 complete gate

## Phase 2 – Fixes
PHASE 2 – FIXES
# | Task | File / Location | Day(s) | Duration | Priority | Status | Notes
CRITICAL SEVERITY
1 | Fix Dockerfile Python 3.11 → 3.12 | Dockerfile line 1 | Day 8 | 30 min | CRITICAL | Done | python:3.11-slim → python:3.12-slim
2 | Merge strategy/ and strategies/ packages | src/delta_exchange_bot/strategy/ | Days 8–10 | 3 days | CRITICAL | Done | Two RSIScalping classes cause shadow bugs
3 | Update all imports after merge | core/engine.py, portfolio.py | Day 10 | 1 day | CRITICAL | Done | Run pytest after — all must pass
4 | Change TRADE_FREQUENCY_S 60 → 5 | .env, core/settings.py | Day 8 | 30 min | CRITICAL | Not Started | Add signal_eval_every=6 setting
5 | Add exchange-native stop orders | api/delta_client.py | Days 14–20 | 6 days | CRITICAL | Not Started | place_stop_limit_order() method
6 | Store stop_order_id in DB | persistence/models.py | Day 15 | 1 day | CRITICAL | Not Started | Add column to Position model
7 | Cancel stop order on position close | execution/order_execution_engine.py | Day 16 | 1 day | CRITICAL | Not Started | Prevent orphaned stop orders
8 | Add idempotent order placement | api/delta_client.py | Day 12 | 1 day | CRITICAL | Done | SHA256(trade_id+symbol+side) as client_order_id
HIGH SEVERITY
9 | Fix RSI Wilder's smoothing formula | strategy/rsi_scalping.py | Days 12–13 | 1 day | HIGH | Done | Currently 7 pts off vs TradingView
10 | Wire YAML config files to Settings | core/settings.py | Days 10–12 | 2 days | HIGH | Done | config/paper.yml currently ignored
11 | Consolidate two risk managers into one | risk/risk_manager.py | Day 11 | 1 day | HIGH | Not Started | Delete advanced_risk_manager.py
12 | Add fill confirmation polling loop | execution/order_execution_engine.py | Day 13 | 1 day | HIGH | Not Started | Poll until filled/rejected/timeout
MEDIUM SEVERITY
13 | Add funding rate awareness | api/delta_client.py, execution/ | Days 20–24 | 4 days | MED | In Progress | get_funding_rate(), log on each trade
14 | Add funding rate cost to PnL calc | execution/fee_manager.py | Day 22 | 1 day | MED | Not Started | Total fee = taker + funding cost
15 | Add max holding period (30 min default) | core/engine.py, core/settings.py | Days 24–26 | 2 days | MED | Done | max_hold_candles=30 setting
16 | Persist ProtectionState to PostgreSQL | persistence/models.py, db.py | Day 20 | 2 days | MED | Not Started | Crash-safe SL/TP recovery
17 | Add crash recovery on startup | core/engine.py | Day 21 | 1 day | MED | Not Started | _recover_state() method
MONITORING
18 | Add Grafana to docker-compose.yml | docker-compose.yml | Days 26–37 | 10 days | MED | Done | + Loki for log aggregation
19 | Import Trading Overview dashboard | Grafana UI | Day 28 | 1 day | MED | Not Started | PnL, win rate, positions
20 | Import Risk Monitor dashboard | Grafana UI | Day 29 | 1 day | MED | Not Started | Drawdown, leverage, daily loss
21 | Import API Health dashboard | Grafana UI | Day 30 | 1 day | MED | Not Started | Request latency, error rate

## Phase 3 – Strategies
PHASE 3 – STRATEGIES
# | Task | File / Location | Day(s) | Duration | Priority | Status | Notes
PRIORITY 1 — VWAP Deviation (Days 38–42)
1 | Create VWAPDeviationStrategy class | strategies/vwap_deviation.py (new) | Day 38 | 2 days | HIGH | Not Started | Entry: price >0.5% from VWAP
2 | Wire to StrategyManager RANGING regime | core/engine.py | Day 40 | 1 day | HIGH | Not Started | Activate for RANGING + LOW_VOL
3 | Backtest on 30 days BTCUSD 1m data | backtesting/ | Day 41 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.5
4 | 48-hour paper run | Terminal | Day 42 | Passive | HIGH | Not Started | Observe signal quality
PRIORITY 2 — Bollinger Bands Squeeze (Days 43–46)
5 | Create BollingerSqueezeStrategy class | strategies/bollinger_squeeze.py (new) | Day 43 | 2 days | HIGH | Not Started | Detect low-vol squeeze before breakout
6 | Wire to StrategyManager LOW_VOL regime | core/engine.py | Day 45 | 1 day | HIGH | Not Started | LOW_VOL → HIGH_VOL transition
7 | Backtest + validate | backtesting/ | Day 46 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.8
PRIORITY 3 — MACD Histogram (Days 47–50)
8 | Create MACDHistogramStrategy class | strategies/macd_histogram.py (new) | Day 47 | 2 days | HIGH | Not Started | MACD(12,26,9) histogram direction
9 | Wire alongside TrendFollowing in TRENDING | core/engine.py | Day 49 | 1 day | HIGH | Not Started | Both strategies active in TRENDING
10 | Backtest + validate | backtesting/ | Day 50 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.8
PRIORITY 4 — Order Book Imbalance (Days 51–56)
11 | Create OrderBookImbalanceStrategy class | strategies/order_book_imbalance.py (new) | Day 51 | 3 days | HIGH | Not Started | Use existing get_orderbook() REST call
12 | Calculate bid/ask ratio top 5 levels | strategies/order_book_imbalance.py | Day 53 | 1 day | HIGH | Not Started | Imbalance > 0.70 = buy signal
13 | Wire as secondary signal all regimes | core/engine.py | Day 54 | 1 day | HIGH | Not Started | Only fetch when primary signal fires
14 | Backtest + validate | backtesting/ | Day 55 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.8
PRIORITY 5 — Multi-Timeframe Confluence (Days 57–62)
15 | Create MultiTimeframeFilter wrapper class | strategies/multi_timeframe_filter.py (new) | Day 57 | 3 days | HIGH | Not Started | 1m + 15m + 1h all must agree
16 | Add fetch_candles(symbol,'1h') support | data/market_data.py | Day 58 | 1 day | MED | Not Started | 1h candles not currently fetched
17 | Apply as filter around all strategies | core/engine.py | Day 60 | 2 days | HIGH | Not Started | Wrap every strategy signal
18 | Test: fewer but higher quality signals | Terminal / Grafana | Day 62 | Passive | HIGH | Not Started | Signal count should drop ~40%
PRIORITY 6 — Funding Rate Extremes (Days 63–68)
19 | Create FundingRateExtremeStrategy class | strategies/funding_rate_extremes.py (new) | Day 63 | 3 days | HIGH | Not Started | Requires Phase 2 get_funding_rate()
20 | +0.1% funding → sell; -0.05% → buy | strategies/funding_rate_extremes.py | Day 65 | 1 day | HIGH | Not Started | Contrarian signal unique to perps
21 | Wire for HIGH_VOL regime | core/engine.py | Day 66 | 1 day | HIGH | Not Started | Activate only in HIGH_VOLATILITY
22 | Backtest + validate | backtesting/ | Day 67 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.8
PRIORITY 7 — Volume-Weighted Momentum (Days 69–72)
23 | Create VolumeWeightedMomentumStrategy | strategies/volume_weighted_momentum.py (new) | Day 69 | 2 days | HIGH | Not Started | 10-bar momentum × volume ratio
24 | Delete old 3-bar MomentumStrategy | strategy/momentum.py | Day 71 | 30 min | HIGH | Not Started | Remove 2/5 rated strategy
25 | Backtest vs old momentum — must be better | backtesting/ | Day 72 | 1 day | HIGH | Not Started | Gate: Sharpe > old version
PRIORITY 8 — S/R Breakout (Days 73–77)
26 | Create SupportResistanceBreakoutStrategy | strategies/sr_breakout.py (new) | Day 73 | 3 days | HIGH | Not Started | 20-bar high/low + volume spike
27 | Wire for TRENDING + HIGH_VOL regimes | core/engine.py | Day 76 | 1 day | HIGH | Not Started | Volume > 1.5× average required
28 | Backtest + validate | backtesting/ | Day 77 | 1 day | HIGH | Not Started | Gate: Sharpe > 0.8
FULL BACKTEST VALIDATION (Days 78–82)
29 | Run all 8 new strategies individually | backtesting/ | Day 78 | 2 days | CRITICAL | Not Started | Only keep if Sharpe > 0.8
30 | Run all 13 strategies together 72 hours | Terminal / Grafana | Days 80–82 | 3 days | CRITICAL | Not Started | Check per-strategy PnL on Grafana

## Phase 4 – Paper Validate
PHASE 4 – PAPER VALIDATE
# | Task | File / Location | Day(s) | Duration | Priority | Status | Notes
MANDATORY VALIDATION — Do NOT skip or shorten
1 | Start 14-day continuous paper run | Terminal | Day 83 | 2 weeks | CRITICAL | Not Started | Must be continuous, no restarts
2 | Day 7 checkpoint: Sharpe > 0.5 | scripts/analyze_paper_trades.py | Day 90 | – | CRITICAL | Not Started | Drawdown < 6% also required
3 | Day 7 checkpoint: Drawdown < 6% | Grafana / analyze script | Day 90 | – | CRITICAL | Not Started | Fail = tune or disable strategies
4 | Weekly run of analyze_paper_trades.py | scripts/analyze_paper_trades.py | Day 90 | 1 hr | HIGH | Not Started | Per-strategy breakdown
5 | Identify losing strategies | Grafana / script output | Day 91 | – | HIGH | Not Started | Tune or disable if consistently negative
6 | Day 14 final gate: Sharpe > 0.8 | scripts/analyze_paper_trades.py | Day 97 | – | CRITICAL | Not Started | Both Day 14 gates MUST pass
7 | Day 14 final gate: Win rate > 45% | scripts/analyze_paper_trades.py | Day 97 | – | CRITICAL | Not Started | Check per-strategy win rates
8 | Day 14 final gate: Max drawdown < 8% | Grafana | Day 97 | – | CRITICAL | Not Started | Hard limit before any live money

## Phase 5 – Cloud Go-Live
PHASE 5 – CLOUD GO-LIVE
# | Task | File / Location | Day(s) | Duration | Priority | Status | Notes
HETZNER SERVER SETUP
1 | Register at hetzner.com | hetzner.com | Day 98 | 30 min | HIGH | Not Started | No credit card needed for signup
2 | Create CX22 server (2vCPU, 4GB, Ubuntu) | Hetzner dashboard | Day 98 | 30 min | HIGH | Not Started | ~₹320/month (~$4)
3 | Set up SSH key for secure access | PowerShell / Hetzner | Day 98 | 1 hr | HIGH | Not Started | Claude guides you through this
4 | Install Python 3.12 + Docker on server | SSH Terminal | Day 99 | 2 hrs | HIGH | Not Started | Same steps as local setup
5 | git clone project to server | SSH Terminal | Day 99 | 30 min | HIGH | Not Started | poetry install on server
6 | Set up production .env (NOT testnet keys) | SSH Terminal | Day 100 | 30 min | CRITICAL | Not Started | DELTA_EXCHANGE_ENV=prod-india
7 | Run live_preflight.py sanity check | scripts/live_preflight.py | Day 100 | 30 min | CRITICAL | Not Started | Final check before going live
GOING LIVE — DO NOT RUSH
8 | Paper mode on cloud server 48 hours | SSH Terminal | Day 101 | 2 days | CRITICAL | Not Started | Must pass before live mode
9 | Set DELTA_MODE=live in server .env | .env on server | Day 103 | 5 min | CRITICAL | Not Started | Only after cloud paper passes
10 | Start at half paper size (ORDER_SIZE=50) | .env on server | Day 103 | 5 min | CRITICAL | Not Started | Scale up only after 10 good live trades
11 | Monitor Grafana intensively first 4 hours | http://server-ip:3000 | Day 103 | 4 hrs | CRITICAL | Not Started | Watch for execution errors
12 | Confirm first real trade + stop on Delta UI | Delta Exchange account | Day 103 | – | CRITICAL | Not Started | Stop order must appear in exchange
13 | Set up systemd auto-restart on reboot | SSH Terminal | Day 104 | 1 hr | HIGH | Not Started | systemctl enable trading-bot
14 | Set up Alertmanager → Telegram alerts | docker-compose.yml | Day 105 | 2 hrs | HIGH | Not Started | Alert on: daily loss > 3%, bot crash

## 📈 Strategy Registry
COMPLETE STRATEGY REGISTRY — 13 STRATEGIES
# | Strategy Name | File | Regime | Rating | Status | Phase Built | Notes
1 | Trend Following (ATR stops) | strategies/trend_following.py | TRENDING | 4/5 ⭐⭐⭐⭐ | Keep | Existing | Best existing strategy — ATR-scaled SL/TP
2 | Mean Reversion (Z-score) | strategies/mean_reversion.py | RANGING / LOW_VOL | 4/5 ⭐⭐⭐⭐ | Keep | Existing | Z-score(20), entry at ±1.5σ deviation
3 | EMA Crossover | strategy/ema_crossover.py | TRENDING | 3/5 ⭐⭐⭐ | Keep + fix | Existing | Add volume filter in Phase 3
4 | RSI Scalping | strategy/rsi_scalping.py | RANGING / HIGH_VOL | 3/5 ⭐⭐⭐ | Fix RSI formula | Phase 2 | Wilder's smoothing fix needed
5 | Momentum (3-bar) | strategy/momentum.py | All regimes | 2/5 ⭐⭐ | REPLACE → #12 | Existing | DELETE after Volume-Weighted Momentum built
6 | VWAP Deviation | strategies/vwap_deviation.py (NEW) | RANGING / LOW_VOL | TBD | Build | Phase 3 | Priority 1 — biggest gap, volume-weighted
7 | Bollinger Bands Squeeze | strategies/bollinger_squeeze.py (NEW) | LOW_VOL → HIGH_VOL | TBD | Build | Phase 3 | Squeeze detector before explosive moves
8 | MACD Histogram Divergence | strategies/macd_histogram.py (NEW) | TRENDING | TBD | Build | Phase 3 | Earlier entries than EMA crossover alone
9 | Order Book Imbalance | strategies/order_book_imbalance.py (NEW) | All (secondary) | TBD | Build | Phase 3 | Signals BEFORE price moves — L2 data
10 | Multi-TF Confluence Filter | strategies/multi_timeframe_filter.py (NEW) | All (filter) | TBD | Build | Phase 3 | 1m + 15m + 1h must all agree direction
11 | Funding Rate Extremes | strategies/funding_rate_extremes.py (NEW) | HIGH_VOL | TBD | Build | Phase 3 | Contrarian — crowded longs/shorts reversal
12 | Volume-Weighted Momentum | strategies/volume_weighted_momentum.py (NEW) | All regimes | TBD | Build | Phase 3 | Replaces #5 — 10-bar × volume ratio
13 | Support / Resistance Breakout | strategies/sr_breakout.py (NEW) | TRENDING / HIGH_VOL | TBD | Build | Phase 3 | 20-bar high/low + volume spike confirmation

## 🐛 Known Issues
KNOWN ISSUES — Fix Before Phase 3
Severity | Issue | File / Location | Fix Phase | Status | Impact | Notes
CRIT | Real API keys committed to GitHub | .env | Phase 1 Day 2 | Not Fixed | Security — exchange account at risk | Delete .env content immediately
CRIT | SL/TP only in memory — lost on crash | execution/order_execution_engine.py | Phase 2 | Not Fixed | Unprotected positions after restart | Place real stop orders on exchange
HIGH | Dockerfile uses Python 3.11 not 3.12 | Dockerfile line 1 | Phase 2 Day 8 | Not Fixed | Docker build will fail | One-line fix
HIGH | RSI Wilder's smoothing wrong (~7 pts) | strategy/rsi_scalping.py | Phase 2 Day 12 | Not Fixed | Wrong entries — RSI off vs TradingView | Replace simple avg with ewm()
HIGH | Duplicate strategy/ and strategies/ | src/ directory | Phase 2 Day 8 | Not Fixed | Two classes with same name → bugs | Merge into strategies/ package
HIGH | TRADE_FREQUENCY_S=60 — too slow | .env | Phase 2 Day 8 | Not Fixed | Scalp opportunities gone by next poll | Change to 5s poll, 30s signal eval
MED | YAML config files ignored by Settings | core/settings.py | Phase 2 Day 10 | Not Fixed | config/paper.yml has no effect | Add from_yaml_and_env() loader
MED | Funding rate costs ignored in PnL | execution/fee_manager.py | Phase 2 Day 20 | Not Fixed | PnL overstated by funding payments | Add to fee calculation
MED | No max holding period for positions | core/engine.py | Phase 2 Day 24 | Not Fixed | Positions can be open forever | 30-candle default (30 min on 1m)
MED | No idempotent order placement | api/delta_client.py | Phase 2 | Not Fixed | Duplicate orders on network retry | SHA256 client_order_id
MED | No fill confirmation polling | execution/order_execution_engine.py | Phase 2 | Not Fixed | Order could be rejected silently | Poll status until filled/timeout
MED | Two risk managers coexist | risk/ | Phase 2 | Not Fixed | Inconsistent behavior, dead code | Delete advanced_risk_manager.py
LOW | No Grafana dashboards | monitoring/ | Phase 2 Day 26 | Not Fixed | Can only see PnL via log files | Add via docker-compose
LOW | No CI/CD pipeline | No .github/workflows/ | Phase 5 | Not Fixed | No automated test on push | Add after cloud migration