## 📊 Dashboard
DELTA EXCHANGE TRADING BOT — PROJECT DASHBOARD
Built with Claude AI • Local to Production • Non-Coder Edition
Phase | Title | Days | Total Tasks | Done | % Complete
Phase 1 | Local Setup & First Run | Days 1–7 | 27 | 0 | 0%
Phase 2 | Fix Critical Issues | Days 8–37 | 30 | 0 | 0%
Phase 3 | 8 New Advanced Strategies | Days 38–82 | 31 | 0 | 0%
Phase 4 | Paper Trading Validation | Days 83–97 | 12 | 0 | 0%
Phase 5 | Cloud Migration & Go Live | Days 98+ | 19 | 0 | 0%
TOTAL PROJECT |  |  | 119
|  |  |  | 0 | 0%
HOW TO USE THIS FILE
1. Work through each phase tab in order (bottom of screen: Phase 1 → Phase 2 → ... → Phase 5)
2. When you complete a task, click the STATUS cell and choose ✅ Done from the dropdown list
3. Use the NOTES column to record: error messages, things Claude said, what you changed
4. The DATE COMPLETED column: type today's date when you tick a task as done
5. Never skip a Critical priority task — they are gates that protect you from losing money
6. If you get stuck on any task: copy the task name + your error message and paste it to Claude
⚠ IMPORTANT: Never use real money until Phase 4 validation gates all pass. No exceptions.

## 🚀 Phase 1 — Setup
PHASE 1 — Local Setup & First Run ¦ Days 1–7
Goal: Bot running in paper mode on your Windows machine within 7 days
Task ID | Task Name | Instructions / What to do | Status | Date Completed
Day 1 — Installation
P1-01 | [CRI] Check Python version | Open PowerShell (Win+X → Terminal). Run: python --version — must show 3.12.x | ☐ To Do
P1-02 | [CRI] Upgrade Python to 3.12 if needed | If version shows 3.11 or lower — tell Claude and follow the upgrade guide | ☐ To Do
P1-03 | [CRI] Verify Poetry is installed | Run: poetry --version — should show 1.8.x or higher | ☐ To Do
P1-04 | [CRI] Install Poetry if missing | Run the Poetry install command Claude gives you in PowerShell. Takes 5 minutes. | ☐ To Do
Day 1–2 — Get the project
P1-05 | [HIG] Navigate to Desktop in PowerShell | Run: cd $env:USERPROFILE\Desktop | ☐ To Do
P1-06 | [HIG] Clone the GitHub repository | Run: git clone https://github.com/vinugani/Trading_Algo.git | ☐ To Do
P1-07 | [HIG] Enter the project folder | Run: cd Trading_Algo | ☐ To Do
P1-08 | [HIG] Open project in VS Code | Run: code . — VS Code opens with all project files in the sidebar | ☐ To Do
P1-09 | [CRI] Install all Python dependencies | Run: poetry install — waits 2–5 minutes, downloads all libraries | ☐ To Do
P1-10 | [HIG] Confirm no red errors in poetry install | Last line should say: Installing the current project: delta-exchange-trading-bot (0.1.0) | ☐ To Do
Day 2 — Security (CRITICAL — do before anything else)
P1-11 | [CRI] Open .env file in VS Code | Click the .env file in the left sidebar | ☐ To Do
P1-12 | [CRI] DELETE all content in .env file | Current file has REAL leaked API keys. Press Ctrl+A then Delete. Remove everything. | ☐ To Do
P1-13 | [CRI] Paste safe paper-mode .env template from Claude | Use the template Claude provides with testnet settings and placeholder keys | ☐ To Do
P1-14 | [CRI] Save the .env file | Press Ctrl+S in VS Code | ☐ To Do
P1-15 | [HIG] Register on Delta Exchange testnet | Go to: cdn-ind.testnet.deltaex.org — create a free account (no real money) | ☐ To Do
P1-16 | [HIG] Generate testnet API key and secret | In testnet account → Settings → API Keys → Create New Key. Copy both values. | ☐ To Do
P1-17 | [CRI] Update .env with your testnet credentials | Replace the placeholder values DELTA_API_KEY and DELTA_API_SECRET with your real testnet keys | ☐ To Do
Day 2 — First run
P1-18 | [CRI] Run the bot in paper mode | Run: poetry run python scripts/run_bot.py --mode paper --strategy portfolio | ☐ To Do
P1-19 | [CRI] Confirm JSON log lines appear in PowerShell | You should see lines like: {"level":"INFO","message":"Starting trading engine in paper mode"} | ☐ To Do
P1-20 | [HIG] Let the bot run for at least 30 minutes | Watch the logs scroll every 60 seconds. This is normal. | ☐ To Do
P1-21 | [HIG] Stop the bot with Ctrl+C | Press and hold Ctrl, then press C. Bot stops cleanly. | ☐ To Do
P1-22 | [MED] Install SQLite Viewer extension in VS Code | Extensions (Ctrl+Shift+X) → search 'SQLite Viewer' by Florian Klampfer → Install | ☐ To Do
P1-23 | [HIG] Open state.db and confirm rows exist | Click state.db in VS Code sidebar. Check trades or signals tables have data rows. | ☐ To Do
Days 3–7 — Observe and understand
P1-24 | [MED] Run bot for 2–3 hours each day | Let it run in paper mode. Don't change anything yet — just observe the output. | ☐ To Do
P1-25 | [HIG] Note any error messages | If you see red text in logs — copy the full error and paste it to Claude to fix | ☐ To Do
P1-26 | [LOW] Ask Claude to explain any log line you don't understand | Understanding the output makes Phase 2 much easier | ☐ To Do
P1-27 | [CRI] ✅ PHASE 1 COMPLETE | Bot runs without errors for 2+ consecutive days. Paper trades recording in state.db. | ☐ To Do
PHASE 1 Summary |  | Total tasks: 27 | 0

## 🔧 Phase 2 — Fixes
PHASE 2 — Fix Critical Issues ¦ Days 8–37
Goal: Security fixed, known bugs corrected, real exchange stops working, Grafana dashboards live
Task ID | Task Name | Instructions / What to do | Status | Date Completed
Day 8 — Quick wins
P2-01 | [HIG] Fix Dockerfile Python version | Open Dockerfile. Change line 1: python:3.11-slim → python:3.12-slim. Save with Ctrl+S. | ☐ To Do
P2-02 | [HIG] Verify Docker fix works | Run: docker build -t test-bot . — should complete without errors | ☐ To Do
Days 8–15 — Code cleanup
P2-03 | [HIG] Merge strategy/ and strategies/ duplicate packages | Claude writes all the unified code. You copy-paste each file Claude provides. | ☐ To Do
P2-04 | [HIG] Run tests after merge | Run: poetry run pytest tests/ — all tests must still pass (green output) | ☐ To Do
P2-05 | [MED] Wire config/paper.yml to Settings class | Claude rewrites core/settings.py to auto-load the YAML config files | ☐ To Do
P2-06 | [MED] Test that YAML config loading works | Change a value in config/paper.yml, restart bot, verify the new value takes effect | ☐ To Do
Days 12–15 — Bug fixes
P2-07 | [HIG] Fix RSI Wilder's smoothing formula | Claude rewrites the _rsi() function in strategies/rsi_scalping.py. Single function change. | ☐ To Do
P2-08 | [HIG] Run RSI unit tests | Run: poetry run pytest tests/unit/test_rsi_scalping_strategy.py | ☐ To Do
P2-09 | [MED] Verify RSI matches TradingView values | Same candle data should now give same RSI as TradingView charts | ☐ To Do
Days 14–20 — Exchange stop orders
P2-10 | [CRI] Add stop-limit order method to DeltaClient | Claude adds place_stop_limit_order() to api/delta_client.py | ☐ To Do
P2-11 | [CRI] Store exchange stop order ID in database | Claude updates open_position_state table schema and the upsert logic | ☐ To Do
P2-12 | [CRI] Place stop order on exchange after every entry | Claude updates _register_entry_position() in cli/professional_bot.py | ☐ To Do
P2-13 | [CRI] Cancel exchange stop order on position close | Claude updates _handle_exit() to cancel the exchange-side stop order | ☐ To Do
P2-14 | [HIG] Test exchange stops in paper mode for 24 hours | Verify stop orders appear in your testnet account on the Delta Exchange website | ☐ To Do
Days 20–24 — Funding rate
P2-15 | [HIG] Add get_funding_rate() to DeltaClient | Claude adds the funding rate API endpoint call to api/delta_client.py | ☐ To Do
P2-16 | [MED] Log funding rate in execution metadata | Claude updates execute_order() to store funding rate in the metadata_json column | ☐ To Do
P2-17 | [HIG] Add funding cost to FeeManager PnL calculation | Claude updates FeeManager to include 8-hour funding charges in profit/loss calculation | ☐ To Do
Days 24–26 — Max holding period
P2-18 | [MED] Add max_hold_candles setting to Settings | Claude adds: max_hold_candles: int = 50 to core/settings.py | ☐ To Do
P2-19 | [MED] Track entry time in open_position_state | Claude adds entry_time column to database and saves it when position opens | ☐ To Do
P2-20 | [MED] Add auto-close logic in process_symbol() | Claude adds the time-based exit check in the main trading loop | ☐ To Do
P2-21 | [MED] Test: verify position auto-closes after time limit | Open a paper position and confirm it closes after max_hold_candles candles | ☐ To Do
Days 26–37 — Grafana dashboards
P2-22 | [HIG] Add Grafana and Loki services to docker-compose.yml | Claude rewrites docker-compose.yml with Grafana + Loki + Promtail services added | ☐ To Do
P2-23 | [HIG] Start full stack: docker compose up -d | Run this in your Trading_Algo folder. All 5 services start. Takes about 2 minutes. | ☐ To Do
P2-24 | [HIG] Open Grafana at http://localhost:3000 | Default login: admin / admin. Change your password when prompted. | ☐ To Do
P2-25 | [HIG] Add Prometheus data source in Grafana | Settings → Data Sources → Add → Prometheus → URL: http://prometheus:9090 → Save | ☐ To Do
P2-26 | [HIG] Import Trading Overview dashboard | Claude provides the JSON. Grafana → Dashboards → Import → paste JSON → Load | ☐ To Do
P2-27 | [HIG] Import Risk Monitor dashboard | Claude provides a second JSON for the risk & drawdown dashboard | ☐ To Do
P2-28 | [MED] Import API Health dashboard | Third dashboard showing API latency, error rates, and circuit breaker status | ☐ To Do
P2-29 | [HIG] Confirm live data flows into dashboards | Run the bot for 30 min, refresh Grafana, see trade_count and PnL metrics update | ☐ To Do
P2-30 | [CRI] ✅ PHASE 2 COMPLETE | Security fixed, bugs corrected, real exchange stops working, Grafana dashboards live. | ☐ To Do
PHASE 2 Summary |  | Total tasks: 30 | 0

## 📈 Phase 3 — Strategies
PHASE 3 — 8 New Advanced Strategies ¦ Days 38–82
Goal: 13 total strategies covering every market regime — all backtested and validated
Task ID | Task Name | Instructions / What to do | Status | Date Completed
Strategy 1 — VWAP Deviation (Days 38–42)
P3-01 | [HIG] Claude writes VWAPDeviationStrategy class | New file: strategies/vwap_deviation.py. Uses volume column from candles DataFrame. | ☐ To Do
P3-02 | [HIG] Add to StrategyManager for RANGING regime | Claude updates strategies/manager.py dispatch. VWAP = most-watched level by pro traders. | ☐ To Do
P3-03 | [HIG] Backtest against 30 days of BTCUSD 1m data | Run BacktestEngine with VWAPDeviationStrategy. Target: Sharpe ratio > 0.5 | ☐ To Do
P3-04 | [MED] Run in paper mode for 48 hours | Observe signal frequency and quality in paper trading logs and Grafana | ☐ To Do
Strategy 2 — Bollinger Bands Squeeze (Days 43–46)
P3-05 | [HIG] Claude writes BollingerSqueezeStrategy class | New file: strategies/bollinger_squeeze.py. Detects volatility coiling before breakouts. | ☐ To Do
P3-06 | [HIG] Add to StrategyManager for LOW_VOL→HIGH_VOL transition | Claude updates manager.py. This strategy watches for regime transition. | ☐ To Do
P3-07 | [HIG] Backtest and validate Sharpe > 0.5 | Run BacktestEngine. Only add to live dispatch if threshold passes. | ☐ To Do
Strategy 3 — MACD Histogram (Days 47–50)
P3-08 | [HIG] Claude writes MACDHistogramStrategy class | New file: strategies/macd_histogram.py. Uses existing EMA functions already in codebase. | ☐ To Do
P3-09 | [HIG] Add to StrategyManager for TRENDING regime | Works alongside existing TrendFollowingStrategy for better trend entries | ☐ To Do
P3-10 | [HIG] Backtest and validate | Compare vs EMA crossover — MACD should show fewer false signals | ☐ To Do
Strategy 4 — Order Book Imbalance (Days 51–56)
P3-11 | [HIG] Claude writes OrderBookImbalanceStrategy class | New file: strategies/order_book_imbalance.py. Uses existing get_orderbook() already in DeltaClient. | ☐ To Do
P3-12 | [HIG] Test bid/ask ratio calculation | Claude writes a small test script to verify the ratio calculates correctly | ☐ To Do
P3-13 | [HIG] Add to StrategyManager as secondary signal for all regimes | This strategy fires BEFORE price moves — unique edge over all other strategies | ☐ To Do
P3-14 | [HIG] Run 2-week paper as validation (hard to backtest) | Order book signals need live validation — monitor in Grafana for 2 weeks | ☐ To Do
Strategy 5 — Multi-Timeframe Confluence (Days 57–62)
P3-15 | [HIG] Add 15m and 1h candle intervals to fetch_candles() | Claude updates data/market_data.py SUPPORTED_INTERVALS to include 15m and 1h | ☐ To Do
P3-16 | [HIG] Claude writes MultiTimeframeFilter class | New file: strategies/multi_timeframe.py. Wraps any existing strategy as a filter. | ☐ To Do
P3-17 | [HIG] Apply MTF filter on top of all existing strategies | Claude updates manager.py to wrap each strategy with the MTF directional filter | ☐ To Do
P3-18 | [HIG] Test: verify fewer but higher-quality signals in paper mode | Signal count should drop ~40% but win rate should increase significantly | ☐ To Do
Strategy 6 — Funding Rate Extremes (Days 63–68)
P3-19 | [HIG] Claude writes FundingRateStrategy class | New file: strategies/funding_rate.py. Uses get_funding_rate() added in Phase 2. | ☐ To Do
P3-20 | [HIG] Add to StrategyManager for HIGH_VOL regime | Extreme positive funding = overleveraged longs = sell signal. Unique crypto edge. | ☐ To Do
P3-21 | [MED] Run paper mode as primary validation | Delta Exchange may have limited history for backtesting funding rates | ☐ To Do
Strategy 7 — Volume-Weighted Momentum (Days 69–72)
P3-22 | [HIG] Claude writes VolumeWeightedMomentumStrategy class | New file: strategies/volume_momentum.py. Replaces the weak 3-bar momentum strategy. | ☐ To Do
P3-23 | [MED] Delete old MomentumStrategy from legacy package | Remove strategy/momentum.py — confirmed no longer used anywhere | ☐ To Do
P3-24 | [HIG] Backtest: compare vs old 3-bar momentum | New version must show better Sharpe ratio. If not, debug the volume multiplier with Claude. | ☐ To Do
Strategy 8 — Support/Resistance Breakout (Days 73–77)
P3-25 | [HIG] Claude writes SupportResistanceBreakoutStrategy class | New file: strategies/sr_breakout.py. 20-bar high/low + volume spike confirmation. | ☐ To Do
P3-26 | [HIG] Add to StrategyManager for TRENDING and HIGH_VOL regimes | Works as second strategy alongside TrendFollowing in trending markets | ☐ To Do
P3-27 | [HIG] Backtest and validate | Target: Sharpe > 0.8, win rate > 50% in trending market conditions | ☐ To Do
Full Validation (Days 78–82)
P3-28 | [HIG] Run BacktestEngine on each of the 8 new strategies individually | Keep a notes file with each strategy's Sharpe ratio, win rate, max drawdown | ☐ To Do
P3-29 | [HIG] Disable any strategy with Sharpe ratio below 0.5 | Ask Claude to help tune parameters before permanently disabling any strategy | ☐ To Do
P3-30 | [HIG] Run all 13 strategies together in paper mode for 72 hours | Monitor Grafana — confirm variety of signals across all 4 market regimes | ☐ To Do
P3-31 | [CRI] ✅ PHASE 3 COMPLETE | All 13 strategies running, backtested, regime dispatch working for all 4 regimes. | ☐ To Do
PHASE 3 Summary |  | Total tasks: 31 | 0

## 🧪 Phase 4 — Validation
PHASE 4 — Paper Trading Validation ¦ Days 83–97
Goal: 2 full weeks of paper trading passing all 3 gates before any real money is involved
Task ID | Task Name | Instructions / What to do | Status | Date Completed
Week 1 (Days 83–90) — Run and monitor
P4-01 | [CRI] Start 14-day continuous paper trading run | Run: poetry run python scripts/run_bot.py --mode paper --strategy portfolio | ☐ To Do
P4-02 | [CRI] Monitor Grafana dashboard every single day | Check each morning: trade_count, win_rate, drawdown, total_pnl, api_errors | ☐ To Do
P4-03 | [CRI] Day 7 gate — Sharpe ratio > 0.5 | Ask Claude to calculate Sharpe from state.db trade data. Must pass to continue. | ☐ To Do
P4-04 | [CRI] Day 7 gate — max drawdown below 6% | Check the drawdown gauge in Grafana Risk Monitor dashboard | ☐ To Do
P4-05 | [HIG] Run analyze_paper_trades.py after Day 7 | Run: poetry run python scripts/analyze_paper_trades.py — review per-strategy results | ☐ To Do
P4-06 | [HIG] Note strategies that consistently lose money | Flag them for parameter tuning in Week 2 | ☐ To Do
Week 2 (Days 91–97) — Tune and confirm
P4-07 | [HIG] Tune underperforming strategies with Claude | Adjust thresholds (e.g. RSI entry from 30 → 35) if a strategy loses too often | ☐ To Do
P4-08 | [CRI] Day 14 gate — Sharpe ratio above 0.8 | MUST pass this gate before proceeding to live trading. No exceptions. | ☐ To Do
P4-09 | [CRI] Day 14 gate — max drawdown below 8% | MUST pass. If drawdown exceeds 8%, return to Phase 3 and fix the problem. | ☐ To Do
P4-10 | [CRI] Day 14 gate — win rate above 45% | At least 45% of paper trades must be profitable over the 2-week period | ☐ To Do
P4-11 | [HIG] Run final analyze_paper_trades.py report | Save the output PDF/text. This is your baseline to compare against live performance. | ☐ To Do
P4-12 | [CRI] ✅ PHASE 4 COMPLETE | All 3 validation gates passed for 2 consecutive weeks. Ready for cloud migration. | ☐ To Do
PHASE 4 Summary |  | Total tasks: 12 | 0

## ☁️ Phase 5 — Go Live
PHASE 5 — Cloud Migration & Go Live ¦ Days 98+
Goal: Bot running 24/7 on Hetzner cloud server, live trading with real money
Task ID | Task Name | Instructions / What to do | Status | Date Completed
Hetzner server setup
P5-01 | [HIG] Register at hetzner.com | Create an account. No upfront payment for registration. | ☐ To Do
P5-02 | [HIG] Create a CX22 server | 2 vCPU, 4GB RAM, 40GB SSD, Ubuntu 22.04. Choose Frankfurt or Helsinki datacenter. | ☐ To Do
P5-03 | [HIG] Set up SSH key for secure access | Claude walks you through generating an SSH key pair on Windows PowerShell | ☐ To Do
P5-04 | [HIG] Connect to server from PowerShell | Run: ssh root@YOUR_SERVER_IP — you should see the Ubuntu command prompt | ☐ To Do
P5-05 | [HIG] Install Python 3.12, Git, Docker on the server | Claude gives you the exact Ubuntu commands. Takes about 10 minutes. | ☐ To Do
P5-06 | [HIG] Clone project on the server | Same git clone command as Phase 1, but now run on the cloud server | ☐ To Do
P5-07 | [CRI] Set up .env with REAL production API keys on server | Use REAL Delta Exchange API keys (NOT testnet). Enable IP whitelist to server IP. | ☐ To Do
P5-08 | [CRI] Enable IP whitelisting for API keys on Delta Exchange | In Delta Exchange account settings, restrict your API key to the server's static IP | ☐ To Do
P5-09 | [CRI] Run live preflight check — must pass ALL checks | Run: poetry run python scripts/live_preflight.py — all items must show green | ☐ To Do
Going live — take it slow
P5-10 | [CRI] Start in paper mode on cloud server first | Confirm the server runs the bot identically to your local machine | ☐ To Do
P5-11 | [CRI] Paper mode passes on cloud server for 48 hours | No errors, normal signal generation, Grafana data flowing from cloud | ☐ To Do
P5-12 | [CRI] Set DELTA_MODE=live and DELTA_ORDER_SIZE=50 in .env | START SMALL: half your normal order size for the first week of live trading | ☐ To Do
P5-13 | [CRI] Start live bot running in background on server | Run: nohup poetry run python scripts/run_bot.py --mode live & | ☐ To Do
P5-14 | [CRI] Monitor Grafana intensively for first 4 hours | Watch every metric. Confirm first real trade shows in your Delta Exchange account. | ☐ To Do
P5-15 | [CRI] Confirm first live trade executes correctly | Check Delta Exchange account for position. Verify size, side, and price are correct. | ☐ To Do
P5-16 | [HIG] Set up systemd service for auto-restart on server reboot | Claude writes the service file. Bot restarts automatically if the server reboots. | ☐ To Do
P5-17 | [HIG] Set up Telegram alerts for critical events | Claude sets up alerts for: drawdown > 3%, kill-switch triggered, position mismatch | ☐ To Do
P5-18 | [MED] Increase order size after first 2 weeks of clean live trading | Only increase from $50 to $100 after seeing 2 clean weeks of live performance | ☐ To Do
P5-19 | [CRI] ✅ PHASE 5 COMPLETE — Production live trading system | Bot running 24/7, live trading, Grafana monitoring, Telegram alerts active. | ☐ To Do
PHASE 5 Summary |  | Total tasks: 19 | 0